## ProjectTeam
Name | GitHub Alias | Role
Dumitru Georgiana Geanina | elly2178 | Developer
Jiménez Norman Alexander | jimen1 | Developer
Schmid Daniel Simon | schmd29 | Scrum Master
Tangarife Bonilla Edison Roberto | tange1 | Developer
Hr. Vogel / Hr. Pfahrer | - | Product Owner

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Configuration | Config Project as Vaadin Project | high | 36 |  | 2 | waiting
2 | Business Logic | Create basic structure logic | high | 36 |  |  | waiting
3 | BYOCS Data Structure | Create Form for Patient | high | 36 |  |  | waiting
4 | MVP for DiaryView | Create basic view for our Data | high | 36 |  |  | waiting
5 | GUI expansion for DiaryView | Add more funtionality, Vaadin Components | low | 36 |  |  | waiting
6 | Doctor View | Create basic view for Doctor, Vaadin Components | medium | 36 |  |  | waiting
7 | Login View | Create a Login GUI | low | 36 |  |  | waiting
8 | To be defined

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Configuration Project | Configure the project in our IDE | Basic Project | Daniel | Alle | High | 4 |  |  | waiting
1.3 | 1 | Code basic Business Logic for Data Diary | Create all the classes and methords for DataDiary | DataStructure Diary | Roberto | Norman | High | 3 |  |  | waiting
1.4 | 1 | Code basic Business Logic for Patient | Create all the classes and methods for Patient | Basic Coding | Georgiana | Roberto | High | 3 |  |  | waiting
1.5 | 1 | Code Basic Business Logic for Doctor and Nurse | Create all the classes for Doctor and Nurse | Basic Coding | Norman | Giorgiana | High | 3 |  |  | waiting
1.6 | 1 | Code Presenter | Code Presenter with Vaadin Components | Basic Coding |  |  | High | 3 |  |  | waiting
1.7 | 1 | Design DiaryView | UI | Main Window |  |  | High | 3 |  |  | waiting
1.8 | 1 | Code DesignView | UI Vaadin | Main Window |  |  | High | 3 |  |  | waiting
1.9 | 1 | Design Doctor View | UI | Doctor View |  |  | medium | 3 |  |  | waiting
1.1 | 1 | Code Doctor View | UI Vaadin | Doctor View |  |  | medium | 3 |  |  | waiting
1.11 | 1 | LoginView | UI | Login View |  |  | low | 3 |  |  | waiting
1.12 | 1 | LoginView | UI Vaadin | Login View |  |  | low | 3 |  |  | waiting
2 |  | To be defined

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2020-11-19 | 36 | 36
2 | 2020-11-26 | 56 | 56
3 | 2020-12-09 | 36 | 36