## ProjectTeam
Name | GitHub Alias | Role
Dumitru Georgiana Geanina | elly2178 | Developer
Jiménez Norman Alexander | jimen1 | Developer
Schmid Daniel Simon | schmd29 | Scrum Master
Tangarife Bonilla Edison Roberto | tange1 | Developer
Hr. Vogel / Hr. Pfahrer | - | Product Owner

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Admit new patient | New Patient visits doctor due to latest OCD episode. Login for the patient is created. New patient record is created. | high | 36 |  |  | work in progress
2 | Tracking patient Data | The patient is all his data for 14 days. During this time he creates a log of his activities. | high | 36 |  |  | work in progress
3 | Doctor tracks the patient | Doctor gets an update from the patient list. | medium | 36 |  |  | waiting
4 | Doctor prescribes a therapy | Doctor is able to assest the data and create a therapy plan. | medium | 36 |  |  | waiting
5 | Doctor interacts with medication | Doctor should be able to prescribe a medication if the patient needs it. | medium | 36 |  |  | waiting

## Sprint Backlog 1
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | IDE Configuration | Project configuration setup for using an IDE | Vaadin, Maven, Jetty | Daniel | All | high | 4 | 10 |  | done
1.2 | 1 | Create Basic Logic | Create needed classes according to class diagram | Java SE | Roberto |  |  | 4 | 4 |  | done
1,2,1 | 1 | Model Classes | Create classes, attributes and getter/setter methods | Java SE | [6 empty] | done
1,2,2 | 1 | Enable routing | Make routing between different views working | Vaadin | Daniel |  |  |  | 2 |  | done
1.3 | 1 | Design login page | Create a login landing site | Vaadin | Daniel |  |  | 4 | 8 |  | work in progress
1.4 | 1 | Admit new Patient | Add Admit new patient functionality | Vaadin | Roberto |  |  | 4 | 2 |  | done
1.5 |  | DB Backend
1.6 | 1 | Create Patient View | Create a view where the patient is able to keep a log | Vaadin | Georgiana |  |  | 4 |  |  | work in progress
1.6.1 | 1 |  | Buttons for the: YSCOB Test, Diary, Patient Mood | Vaadin | Georgiana |  |  | 4 |  |  | work in progress
1.7 | 1 | Patient Log data persistance | Localy Store a Diary in CSV document. | Java SE |  |  |  | 4 |  |  | waiting
1.8 | 1 | Doctor View that enables to read a patient log | Read stored logs up to date. | Vaadin, Java |  |  |  | 4 |  |  | waiting
1.9 | 1 | Doctor View that enables assestment | View where the doctor can write documentation and send a therapy. | Vaadin |  |  |  | 4 |  |  | waiting
1.1 | 1 | Patient can read therapy | In the patient view the therapy should be displayed |  |  |  |  | 4 |  |  | waiting

## Sprint Backlog 2
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 2 | Design login page | Create a login page which navigates to an appropriate page after successful login |  |  |  |  | 9 | 12
1.1.1 |  |  | View | Vaadin | Daniel | Norman | medium | 3 | 4 |  | done
1.1.2 |  |  | Presenter |  | Daniel | Norman | medium | 3 | 4 |  | done
1.1.3 |  |  | Model | Java EE | Daniel | Norman | medium | 3 | 4 |  | done
1.2 | 2 | Admit new Patient | Create a page where a new patient can be created |  |  |  |  | 12 | 14
1.2.1 |  |  | View | Vaadin | Roberto |  | high | 4 | 6 |  | done
1.2.2 |  |  | Presenter |  | Roberto |  | high | 4 | 4 |  | done
1.2.3 |  |  | Model | Java EE | Roberto |  | high | 4 | 4 |  | done
1.3 | 2 | Patient screen | Buttons for the: YSCOB Test, Patient Mood | Vaadin |  |  |  | 12 | 14
1,3,1 |  |  | View | Vaadin | Georgiana |  | high | 4 | 3 |  | done
1,3,2 |  |  | Presenter |  | Georgiana |  | high | 4 | 8 |  | done
1,3,3 |  |  | Model | Java EE | Georgiana |  | high | 4 | 3 |  | done
1.4 | 2 | Persistence layer | Configure project for postgres database and prepare persistence layer to connect |  |  |  |  | 7
1,4,1 |  |  | Update class diagram | UML | Norman | Daniel | high | 2 | 2 |  | done
1,4,2 |  |  | Implement JPA Repository | Java EE | Norman | Daniel | high | 4 | 4 |  | done
1,4,3 |  |  | Reach database breakthrough | Java EE / SQL | Norman | Daniel | high | 4 | 4 |  | done
1.5 | 2 | Patient screen | Refactor Diaries into MVP pattern |  |  |  |  | 8
|  |  | View | Vaadin | Georgiana |  | medium |  |  |  | done
|  |  | Presenter |  | Georgiana |  | medium |  |  |  | done
|  |  | Model |  | Georgiana |  | medium |  |  |  | done
1.6 | 2 | Unit Testing | Provide Unit Testing for the developped model classes | JUnit | everyone |  |  | 8
Unit test kein separate task --> reinbringen
Funktional and not general --> aka unittest for moodtest

## Sprint Backlog 3
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 3 | Admit new Patient | Create a page where a new patient can be created
1.1.1 |  |  | Add event listeners to components e.g. ButtonClick for Save | View | Roberto | Georgiana | High | 2 | 3 |  | done
1.1.2 |  |  | Listen to event, delegate action to model | Presenter | Roberto | Georgiana | High | 1 | 1 |  | done
1.1.3 |  |  | Refactor into MVP pattern | View | Roberto | Georgiana | High | 2 | 3 |  | done
1.1.4 |  |  | Validate user input | Model | Roberto | Georgiana | Medium | 1 | 0 |  | done
1.1.5 |  |  | Persist patient in database | Model | Roberto (?) | Georgiana | Medium | 1 | 3 |  | in progress
1.1.6 |  |  | Create Unit test for Model | Model | Roberto | Georgiana | Medium | 1 | 0 |  | in progress
1.1.7 |  |  | Add java doc to your code | everywhere | Roberto | Georgiana | Low | 1 | 1 |  | done
1.2 | 3 | Patient screen | Documentation for YSCOB , Mood, Diary |  |  |  |  | 3 | 0
1.2.1 |  |  | View - Documentation (Class documentation) | View | Georgiana | Robert | Low | 1 |  |  | done
1.2.2 |  |  | Presenter - Documentation (Class documentation) | Presenter | Georgiana | Robert | Low | 1 | 0 |  | done
1.2.3 |  |  | Model- Documentation | Model | Georgiana | Robert | Low | 1 | 0 |  | done
1.2.4 |  |  | Add java doc to your code | everywhere | Georgiana | Robert | Low
1.3 | 3 | Persistence layer | Configure project for postgres database and prepare persistence layer to connect |  |  |  |  | 7
1,3,1 |  |  | Remove unused code, clean up, do some renamings | Persistence | Daniel | Norman | Medium | 2 |  |  | in progress
1,3,2 |  |  | Split code into different Repositories | Persistence | Daniel | Norman | Medium | 4 |  |  | in progress
1,3,3 |  |  | Add person table | PostgreSQL | Daniel | Norman | Medium | 2 |  |  | in progress
1.3.4 |  |  | Add java doc to your code | everywhere | Daniel | Norman | Low | 2 |  |  | done
1.4 | 3 | Introduce logging | Add logging function in several classes to track errors
1.4.1 |  |  | Add some error handling | everywhere | Daniel
1.4.2 |  |  | Add logging in persistence | everywhere | Daniel
1.5 | 3 | Patient detail screen | When selecting a patient in PatientOverview, a detail view should be displayed
1.5.1 |  |  | Create a read-only form where patient data is displayed | View | Norman |  | Medium | 2 |  |  | waiting
1.5.2 |  |  | Add to this read-only form the link to his diaries | View | Norman |  | Medium | 2 |  |  | waiting
1.5.3 |  |  | Add to this read-only form the link to his mood / ybocs tests | View | Norman |  | Low | 2 |  |  | waiting
1.5.4 |  |  | Add java doc to your code | everywhere | Norman |  | Low |  |  |  | waiting
1.6 | 3 | Logout Bug | After every logout, the last active view is still rendered, Furthrmore, the url is not updated | View | Daniel |  | High | 2

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2020-11-19 | 36 | 36
2 | 2020-11-26 | 56 | 56
3 | 2020-12-09 | 36 | 36